## Overview
Field | Value | Notes
Working Title | Titles: A LitRPG Progression Mod | Rename freely - the mod id below is what matters for code
Mod ID | titles | Lowercase a-z0-9_ only. Check it is unused on Modrinth/CurseForge before committing
Concept | Players earn persistent Titles for in-game accomplishments. Titles grant passive stat bonuses and unique powers. | Collection + prestige + build customization
Core Loop | Play normally -> hit a hidden or public milestone -> earn Title -> equip it in the Titles screen -> gain a passive bonus -> chase rarer Titles
Equip Model | 10 equip slots capped at a 40-point power budget. Unique and Limited titles stack on top - slot-exempt and budget-exempt. | DECIDED. See the Balance Model sheet
Audience | Multiplayer-first. Single player must work identically. | DECIDED. Server-authoritative code makes SP free via the integrated server
Target Game Version | 1.20.1 - DECIDED | Forced by integration. Every mod we want to hook into is Forge 1.20.1 only. Compatibility with them is the one requirement that cannot be engineered around - everything else can. 1.20.1 also still carries one of the two largest modded populations so this is not an exile.
Upgrade Path | Ship 1.20.1 v1 first - then ONE jump straight to the current stable version. Skip every intermediate. | Nobody plays 1.20.4 or 1.21.3. One port with a finished playtested mod in hand beats five ports with a half-built one. Do not pin the port target now - aim at whatever is stable when we get there.
Mod Loader | Forge 47.x on 1.20.1 - NeoForge on the port - DECIDED | Supersedes the earlier NeoForge-only decision. Integration targets are Forge-only so we have no choice on 1.20.1. Consequence - the port crosses a loader change AND five years of API churn in a single jump. See the Forward compatibility rows on the Design Decisions sheet.
JDK Required | Java 17 | 1.20.1 will not build on a newer toolchain. You already have 17 installed so nothing to do. The port target will want 21 or newer - install that at port time not now.
Mappings | Official (Mojang) plus Parchment for parameter names | 1.20.1 is obfuscated - there is a real mapping layer. Parchment supplies readable parameter names on top of it. The port target is fully unobfuscated so mappings stop mattering entirely after the jump.
Language Level | Java 17 syntax only | Records - sealed interfaces and switch expressions all exist in 17 and all survive the port unchanged. Nothing newer is worth using if it makes the source move badly.
Build Tool | Gradle plus ForgeGradle 6 | ModDevGradle is NeoForge-only and does not apply on 1.20.1. The build script is thrown away at port time regardless - do not over-invest in it.
Sided-ness | Server-authoritative. Client is display only. | All title grants/checks run on the logical server and sync via packets
Persistence - Per Player | Forge Capability wrapping a plain codec-backed record | The record is the real data - the capability is only a holder. On NeoForge that same record drops into a Data Attachment untouched. Survives death via PlayerEvent.Clone - Forge does not copy it for you.
Persistence - Per World | SavedData / PersistentState on the overworld | Holds the server-wide ledger for Limited and Unique titles
Integration Targets | Forge 1.20.1 mods - exact list still to be pinned | See Open Question 16. Every one must be a SOFT dependency behind a mod-loaded guard. The mod has to load and play correctly with all of them absent.
Port Discipline | Confine the Forge API behind a small platform layer | Five or six interfaces - registration - networking - persistence - events - attributes - screen glue. Not a framework. Every direct Forge call is a port cost. See Design Decisions.
Data-driven? | Yes - titles defined in JSON under data/<namespace>/title/ | Lets you and datapack authors add titles without recompiling
Config | Server config (balance, scarcity toggles) + client config (HUD position) | Keep balance numbers out of code
Min Viable Scope | ~12 titles, 4 effect types, 1 screen, 1 keybind | Ship this before writing 60 titles
Stretch Scope | Title sets/synergies, seasonal resets, leaderboard, chat prefix, nameplate render
Biggest Technical Risk | Server-wide Limited/Unique title claims must be race-free and survive crashes | Single-threaded server tick makes this tractable - just do not do it async
Biggest Design Risk | Limited-quantity titles create FOMO and grief in multiplayer | See the Design Decisions sheet for mitigations

## Titles
ID | Display Name | Category | Rarity | Scarcity | Max Holders | Secret | Hint | How to Obtain | Progress Source | Effect Summary | Effect Types | Magnitude | Power Budget | Impl Complexity | Status | Flavor Text
novice | Novice | Starter | Common | Unlimited | - | No | - | Granted on first join if the random roll gives nothing better | First-join grant | Small all-round nudge for new characters | ATTR_MAX_HEALTH | +2.0 max health | 2 | Easy | Planned | Everyone starts somewhere.
wanderer | Wanderer | Starter | Common | Unlimited | - | No | - | Possible random starter title | First-join grant | Slightly faster on foot | ATTR_MOVEMENT_SPEED | +4% | 2 | Easy | Planned | The road was there before you were.
tinkerer | Tinkerer | Starter | Common | Unlimited | - | No | - | Possible random starter title | First-join grant | Tools last a little longer | CUSTOM | -10% durability consumption | 2 | Medium | Planned | Fix it twice and it never breaks.
forager | Forager | Starter | Common | Unlimited | - | No | - | Possible random starter title | First-join grant | Food restores slightly more saturation | CUSTOM | +15% saturation from food | 2 | Medium | Planned | The forest sets a table for those who look.
scrapper | Scrapper | Starter | Common | Unlimited | - | No | - | Possible random starter title | First-join grant | Bare-fist damage up | ATTR_ATTACK_DAMAGE | +1.0 when empty-handed | 2 | Medium | Planned | No sword? No problem.
stone_breaker | Stone Breaker | Mining | Common | Unlimited | - | No | - | Break 10 stone-family blocks with an empty hand | Vanilla stat BLOCK_MINED + empty-hand check | Bare hands break stone-tier blocks at stone pickaxe speed and they drop properly | TOOL_TIER_HAND ATTR_BLOCK_BREAK_SPEED | Hand = stone tier speed and drops | 3 | Hard | Planned | Knuckles like gravel.
pick_hand | Pick Hand | Mining | Common | Unlimited | - | No | - | Mine 2000 blocks with a pickaxe | Vanilla stat BLOCK_MINED | Pickaxes swing faster | TOOL_PROFICIENCY | +20% pickaxe break speed | 3 | Medium | Planned | The handle wore down to fit your grip.
iron_knuckles | Iron Knuckles | Mining | Rare | Unlimited | - | No | - | Break 40 blocks by hand after earning Stone Breaker | Custom counter | Bare hands reach iron tier | TOOL_TIER_HAND | Hand = iron tier speed and drops | 6 | Hard | Planned | You stopped noticing the blood.
deepslate_delver | Deepslate Delver | Mining | Uncommon | Unlimited | - | No | - | Mine 500 deepslate | Vanilla stat BLOCK_MINED | Faster mining below sea level | ATTR_BLOCK_BREAK_SPEED | +15% while below y=0 | 3 | Medium | Planned | The stone gets meaner the deeper you go.
vein_seeker | Vein Seeker | Mining | Rare | Unlimited | - | No | - | Mine 250 ore blocks of any type | Vanilla stat BLOCK_MINED over an ore tag | Chance at extra ore drops | ON_MINE_PROC ATTR_LUCK | 8% double drop and +1 luck | 5 | Medium | Planned | You can hear where the metal sleeps.
spelunker | Spelunker | Mining | Uncommon | Unlimited | - | No | - | Spend 10 in-game days below y=-40 | Tick sampler every 100 ticks | Faint sight in total darkness | PASSIVE_EFFECT | Night Vision while below y=0 | 3 | Medium | Planned | Daylight is a rumor down here.
quarrymaster | Quarrymaster | Mining | Epic | Limited | 3 | No | - | Mine 40000 blocks total | Vanilla stat sum | SIGNATURE - mining mastery. Utility only - no combat power. | ATTR_BLOCK_BREAK_SPEED ATTR_MINING_EFFICIENCY | +20% speed and +2 efficiency | 4 exempt | Easy | Planned | The mountain lost.
obsidian_willed | Obsidian Willed | Mining | Rare | Unlimited | - | No | - | Mine 64 obsidian | Vanilla stat BLOCK_MINED | Resistant to explosions | DMG_VS_DAMAGE_SOURCE ATTR_EXPLOSION_KB_RESIST | -25% explosion damage and +0.5 explosion kb resist | 5 | Medium | Planned | Slow to break. Slower to bend.
woodcutter | Woodcutter | Gathering | Common | Unlimited | - | No | - | Chop 500 logs | Vanilla stat BLOCK_MINED over the logs tag | Axes bite deeper | TOOL_PROFICIENCY | +25% axe break speed | 3 | Medium | Planned | The forest is just a queue.
groundskeeper | Groundskeeper | Gathering | Common | Unlimited | - | No | - | Dig 2000 dirt-family blocks | Vanilla stat BLOCK_MINED over a tag | Shovels move more | TOOL_PROFICIENCY | +25% shovel break speed | 3 | Medium | Planned | Somebody has to move the hill.
undead_bane | Undead Bane | Combat | Common | Unlimited | - | No | - | Kill 100 zombies | Vanilla stat ENTITY_KILLED | More damage to the whole undead tag | DMG_VS_TYPE | +15% vs undead entity type tag | 4 | Medium | Planned | They keep coming. So do you.
web_cutter | Web Cutter | Combat | Common | Unlimited | - | No | - | Kill 100 spiders | Vanilla stat ENTITY_KILLED | More damage to arthropods and immunity to web slowdown | DMG_VS_TYPE CUSTOM | +15% vs arthropods and normal speed in cobwebs | 4 | Medium | Planned | Eight legs. Same result.
drowned_hunter | Drowned Hunter | Combat | Common | Unlimited | - | No | - | Kill 100 drowned | Vanilla stat ENTITY_KILLED | More damage to drowned | DMG_VS_TYPE | +10% vs drowned | 2 | Easy | Planned | They were sailors once.
husk_breaker | Husk Breaker | Combat | Common | Unlimited | - | No | - | Kill 75 husks | Vanilla stat ENTITY_KILLED | More damage to husks | DMG_VS_TYPE | +10% vs husks | 2 | Easy | Planned | The desert mummifies its mistakes.
bogged_hunter | Bogged Hunter | Combat | Common | Unlimited | - | No | - | Kill 50 bogged | Vanilla stat ENTITY_KILLED | More damage to bogged | DMG_VS_TYPE | +10% vs bogged | 2 | Easy | Planned | Something rotted and kept the bow.
ashen_reaper | Ashen Reaper | Combat | Common | Unlimited | - | No | - | Kill 50 wither skeletons | Vanilla stat ENTITY_KILLED | More damage to wither skeletons | DMG_VS_TYPE | +10% vs wither skeletons | 2 | Easy | Planned | The fortress keeps making more.
piglin_bruiser | Piglin Bruiser | Combat | Common | Unlimited | - | No | - | Kill 100 piglins or piglin brutes | Vanilla stat ENTITY_KILLED | More damage to piglins | DMG_VS_TYPE | +10% vs piglins and piglin brutes | 2 | Easy | Planned | Gold only buys so much patience.
hoglin_hunter | Hoglin Hunter | Combat | Common | Unlimited | - | No | - | Kill 50 hoglins or zoglins | Vanilla stat ENTITY_KILLED | More damage to hoglins | DMG_VS_TYPE | +10% vs hoglins and zoglins | 2 | Easy | Planned | Pork chops with a temper.
ghast_swatter | Ghast Swatter | Combat | Common | Unlimited | - | No | - | Kill 25 ghasts | Vanilla stat ENTITY_KILLED | More damage to ghasts | DMG_VS_TYPE | +10% vs ghasts | 2 | Easy | Planned | Crying does not help either of you.
witch_hunter | Witch Hunter | Combat | Common | Unlimited | - | No | - | Kill 50 witches | Vanilla stat ENTITY_KILLED | More damage to witches | DMG_VS_TYPE | +10% vs witches | 2 | Easy | Planned | She drank the wrong one.
slime_splitter | Slime Splitter | Combat | Common | Unlimited | - | No | - | Kill 100 slimes or magma cubes | Vanilla stat ENTITY_KILLED | More damage to slimes | DMG_VS_TYPE | +10% vs slimes and magma cubes | 2 | Easy | Planned | Halving a problem is not solving it.
phantom_swatter | Phantom Swatter | Combat | Common | Unlimited | - | No | - | Kill 50 phantoms | Vanilla stat ENTITY_KILLED | More damage to phantoms | DMG_VS_TYPE | +10% vs phantoms | 2 | Easy | Planned | Go to bed.
guardian_diver | Guardian Diver | Combat | Common | Unlimited | - | No | - | Kill 50 guardians | Vanilla stat ENTITY_KILLED | More damage to guardians | DMG_VS_TYPE | +10% vs guardians and elder guardians | 2 | Easy | Planned | The temple stares back.
exterminator | Exterminator | Combat | Common | Unlimited | - | No | - | Kill 100 silverfish or endermites | Vanilla stat ENTITY_KILLED | More damage to infestation mobs | DMG_VS_TYPE | +10% vs silverfish and endermites | 2 | Easy | Planned | Check the walls. Always check the walls.
vex_swatter | Vex Swatter | Combat | Common | Unlimited | - | No | - | Kill 50 vexes | Vanilla stat ENTITY_KILLED | More damage to vexes | DMG_VS_TYPE | +10% vs vexes | 2 | Easy | Planned | Small. Fast. Rude.
breeze_catcher | Breeze Catcher | Combat | Common | Unlimited | - | No | - | Kill 25 breezes | Vanilla stat ENTITY_KILLED | More damage to breezes | DMG_VS_TYPE | +10% vs breezes | 2 | Easy | Planned | You cannot punch wind. You did anyway.
shulker_cracker | Shulker Cracker | Combat | Common | Unlimited | - | No | - | Kill 30 shulkers | Vanilla stat ENTITY_KILLED | More damage to shulkers | DMG_VS_TYPE | +10% vs shulkers | 2 | Easy | Planned | A box with opinions.
ravager_breaker | Ravager Breaker | Combat | Common | Unlimited | - | No | - | Kill 25 ravagers | Vanilla stat ENTITY_KILLED | More damage to ravagers | DMG_VS_TYPE | +10% vs ravagers | 2 | Easy | Planned | It stopped. Eventually.
bone_splitter | Bone Splitter | Combat | Uncommon | Unlimited | - | No | - | Kill 100 skeletons | Vanilla stat ENTITY_KILLED | More damage to skeletons and less from arrows | DMG_VS_TYPE DMG_RESIST_FROM_TYPE | +15% vs skeletal and -10% projectile damage | 5 | Medium | Planned | Aim for the ribs. There is nothing else there.
creeper_defuser | Creeper Defuser | Combat | Rare | Unlimited | - | No | - | Kill 50 creepers without dying to one | Kill counter with a death reset | Creepers barely scratch you | DMG_RESIST_FROM_TYPE DMG_VS_TYPE | -40% creeper explosion damage and +15% vs creepers | 6 | Medium | Planned | That hiss used to mean something.
ender_hunter | Ender Hunter | Combat | Uncommon | Unlimited | - | No | - | Kill 20 endermen | Vanilla stat ENTITY_KILLED | More damage to endermen | DMG_VS_TYPE | +20% vs endermen | 5 | Easy | Planned | Look. Just do not blink.
blaze_quencher | Blaze Quencher | Combat | Rare | Unlimited | - | No | - | Kill 50 blazes | Vanilla stat ENTITY_KILLED | Fire resistance and damage vs nether mobs | ATTR_BURNING_TIME DMG_VS_TYPE | -60% burn time and +15% vs blazes | 5 | Medium | Planned | Cool under pressure.
raid_breaker | Raid Breaker | Combat | Epic | Unlimited | - | No | - | Win 5 village raids | Vanilla advancement hero_of_the_village | Damage vs illagers and better villager prices | DMG_VS_TYPE CUSTOM | +20% vs illagers and -15% trade cost | 6 | Hard | Planned | The bells stopped ringing when you arrived.
shieldbearer | Shieldbearer | Combat | Uncommon | Unlimited | - | No | - | Block 500 damage with a shield | Custom counter on shield block | Tougher and steadier | ATTR_ARMOR_TOUGHNESS ATTR_KNOCKBACK_RESIST | +2 toughness and +0.2 kb resist | 5 | Medium | Planned | A wall that walks.
duelist | Duelist | Combat | Epic | Unlimited | - | No | - | Land 100 fully-charged critical hits | Attack event with crit flag | Crits hit harder | CUSTOM | +30% critical hit damage | 6 | Medium | Planned | Timing beats strength.
berserker | Berserker | Combat | Epic | Unlimited | - | No | - | Kill 25 hostile mobs while below 4 hearts | Kill event with health check | Damage scales as health drops | ON_HURT_PROC ATTR_ATTACK_DAMAGE | Up to +30% damage below 30% HP | 7 | Medium | Planned | Pain is just information.
berserker_unlimited | Berserker Unlimited | Combat | Mythic | Unlimited | - | Yes | Something in you stopped flinching a long time ago. | Kill 100 hostile mobs while at or below 2 hearts | Kill event with a health check | Permanently faster and hitting harder - no low-health condition on the payout | ATTR_ATTACK_DAMAGE ATTR_MOVEMENT_SPEED | +15% damage and +10% movement speed | 7 | Medium | Planned | Two hearts is plenty. You have not needed more in a long time.
marksman | Marksman | Combat | Rare | Unlimited | - | No | - | Kill 50 mobs with a bow from over 30 blocks | Projectile kill event with distance | Arrows fly truer and hit harder | CUSTOM | +15% projectile damage and reduced arrow drop | 6 | Hard | Planned | The wind is a suggestion.
dragonslayer | Dragonslayer | Combat | Legendary | Unlimited | - | No | - | Kill the Ender Dragon | Vanilla stat ENTITY_KILLED | Broad combat mastery | ATTR_ATTACK_DAMAGE ATTR_MAX_HEALTH | +10% damage and +12 max health | 7 | Easy | Planned | It was big. You were stubborn.
first_dragonslayer | First Dragonslayer | Combat | Unique | Unique | 1 | No | - | Be the first player on this world to kill the Ender Dragon | Server ledger claim | SIGNATURE - never take fall damage. Small combat edge on top. | CUSTOM ATTR_ATTACK_DAMAGE | Fall damage immunity and +5% damage | 4 exempt | Medium | Planned | There is only ever one first.
monster_slayer | Monster Slayer | Combat | Unique | Founding | 10 | Yes | Eradication of these fiends is the only solution... | Be one of the first 10 players on the server to kill 150 of every standard hostile mob - list defined in the datapack - bosses excluded | Vanilla stat ENTITY_KILLED checked per type against the datapack list - server ledger claim | SIGNATURE - broad mastery over every monster in the world. Does nothing in PvP. | DMG_VS_TYPE | +20% vs all hostile mobs - never vs players | 5 exempt | Medium | Planned | Nothing in the dark is new to you anymore.
wither_bane | Wither Bane | Combat | Legendary | Unlimited | - | No | - | Kill the Wither | Vanilla stat ENTITY_KILLED | Immune to wither and stronger against bosses | CUSTOM DMG_VS_TYPE | Wither effect immunity and +10% vs bosses | 9 | Medium | Planned | Three heads. No survivors.
healthy | Healthy | Survival | Common | Unlimited | - | No | - | Keep the hunger bar full for 3 consecutive in-game days | Tick sampler on food level | Two extra hearts | ATTR_MAX_HEALTH | +4.0 max health | 4 | Easy | Planned | Three square meals and a long nap.
heat_hardened | Heat Hardened | Survival | Common | Unlimited | - | No | - | Take 200 total fire or lava damage and live | Damage source counter | Fire hurts less and ends sooner | DMG_VS_DAMAGE_SOURCE ATTR_BURNING_TIME | -10% fire damage and -25% burn time | 3 | Easy | Planned | You have been on fire enough times to have a routine.
cold_hardened | Cold Hardened | Survival | Common | Unlimited | - | No | - | Take 100 total freezing damage | Damage source counter | Freezing hurts less | DMG_VS_DAMAGE_SOURCE | -15% freeze damage | 2 | Easy | Planned | Shivering is just a bad habit.
blast_hardened | Blast Hardened | Survival | Common | Unlimited | - | No | - | Survive 25 explosions | Damage source counter | Explosions hurt less | DMG_VS_DAMAGE_SOURCE | -10% explosion damage | 2 | Easy | Planned | Ears still ringing. Worth it.
arrow_reader | Arrow Reader | Survival | Common | Unlimited | - | No | - | Take 100 arrow hits | Damage source counter | Projectiles hurt less | DMG_VS_DAMAGE_SOURCE | -10% projectile damage | 2 | Easy | Planned | You watch the hands - not the arrow.
hard_headed | Hard Headed | Survival | Common | Unlimited | - | No | - | Be hit by 20 falling blocks | Damage source counter | Falling blocks barely register | DMG_VS_DAMAGE_SOURCE | -50% falling block damage | 2 | Easy | Planned | The anvil lost.
venom_tested | Venom Tested | Survival | Common | Unlimited | - | No | - | Spend 10 real minutes poisoned | Tick sampler on active effects | Poison and magic damage hurt less | DMG_VS_DAMAGE_SOURCE | -25% poison and magic damage | 2 | Easy | Planned | Everything is a dosage question. This is the low end.
well_rested | Well Rested | Survival | Common | Unlimited | - | No | - | Sleep through 30 nights | Sleep event counter | Constant low-grade regeneration | PASSIVE_EFFECT | Regeneration I at all times | 3 | Medium | Planned | Eight hours changes a person.
ironclad | Ironclad | Survival | Common | Unlimited | - | No | - | Wear a full set of iron armor for 3 in-game days | Tick sampler on armor slots | Armor works better | ATTR_ARMOR | +1.5 armor | 3 | Easy | Planned | Heavy is comforting.
deep_breather | Deep Breather | Survival | Common | Unlimited | - | No | - | Spend 30 minutes underwater | Tick sampler while submerged | Longer breath and no underwater mining penalty | ATTR_OXYGEN_BONUS ATTR_SUBMERGED_MINING | +3 oxygen and +0.5 submerged mining | 3 | Easy | Planned | Lungs like a bellows.
cliffhanger | Cliffhanger | Survival | Uncommon | Unlimited | - | No | - | Survive 20 falls that deal damage | Damage source counter | Falls hurt much less | ATTR_SAFE_FALL_DISTANCE ATTR_FALL_DAMAGE_MULT | +4 safe fall and -35% fall damage | 4 | Easy | Planned | Gravity keeps trying. Gravity keeps failing.
frostborn | Frostborn | Survival | Uncommon | Unlimited | - | No | - | Spend 5 in-game days in a snowy biome | Tick sampler with biome check | Immune to powder snow freezing and faster on ice | CUSTOM ATTR_MOVEMENT_SPEED | Freeze immunity and +10% speed on ice | 4 | Medium | Planned | The cold gave up on you.
fireproof | Fireproof | Survival | Rare | Unlimited | - | No | - | Survive being in lava for 10 seconds total | Damage source counter | Burns end quickly and hurt less | ATTR_BURNING_TIME DMG_VS_DAMAGE_SOURCE | -70% burn time and -25% fire damage | 5 | Medium | Planned | You smell like a forge and you like it.
famine_walker | Famine Walker | Survival | Rare | Unlimited | - | Yes | Nobody ever earned this on a full stomach. | Survive 1 in-game day at zero hunger without dying | Tick sampler on food level | Hunger drains much slower | CUSTOM | -40% exhaustion rate | 5 | Medium | Planned | You forgot what full feels like.
unbroken | Unbroken | Survival | Legendary | Unlimited | - | No | - | Survive 50 in-game days without dying | Playtime stat minus death reset | Substantially tougher | ATTR_MAX_HEALTH ATTR_ARMOR | +6 max health and +2 armor | 8 | Medium | Planned | Fifty days is a long time to be careful.
the_immortal | The Immortal | Survival | Mythic | Limited | 10 | No | - | Survive 150 in-game days without a single death | Playtime stat minus death reset | SIGNATURE - one free cheat of death per in-game day | CUSTOM ATTR_MAX_HEALTH | Totem-style revive on a 1 in-game day cooldown and +2 max health | 4 exempt | Hard | Planned | Death has stopped filing the paperwork.
sprinter | Sprinter | Exploration | Common | Unlimited | - | No | - | Sprint 20000 blocks | Vanilla stat SPRINT_ONE_CM | Sprinting costs less food | CUSTOM | -25% sprint exhaustion | 2 | Medium | Planned | Second wind arrived early and stayed.
climber | Climber | Exploration | Common | Unlimited | - | No | - | Climb 5000 blocks of ladder or vine | Vanilla stat CLIMB_ONE_CM | Faster on ladders and vines | CUSTOM | +50% climb speed | 2 | Medium | Planned | Up is just sideways with commitment.
boatwright | Boatwright | Exploration | Common | Unlimited | - | No | - | Travel 10000 blocks by boat | Vanilla stat BOAT_ONE_CM | Boats move faster | CUSTOM | +15% boat speed | 2 | Medium | Planned | Two planks and an opinion about water.
rider | Rider | Exploration | Common | Unlimited | - | No | - | Travel 10000 blocks mounted | Vanilla stat HORSE_ONE_CM | Mounts move faster | CUSTOM | +10% mount speed | 2 | Medium | Planned | You stopped holding on years ago.
light_footed | Light Footed | Exploration | Common | Unlimited | - | No | - | Sneak 2000 blocks | Vanilla stat CROUCH_ONE_CM | Sneak without the crawl | ATTR_SNEAKING_SPEED | +30% sneaking speed | 1 | Easy | Planned | Quiet and quick are not opposites.
cartographer | Cartographer | Exploration | Uncommon | Unlimited | - | No | - | Visit 10 distinct biomes | Custom biome-visited set | Faster travel on foot | ATTR_MOVEMENT_SPEED ATTR_STEP_HEIGHT | +8% speed and +0.5 step height | 4 | Medium | Planned | The blank spaces are getting smaller.
ocean_born | Ocean Born | Exploration | Uncommon | Unlimited | - | No | - | Travel 20000 blocks by boat or swimming | Vanilla distance stats | Move well in water | ATTR_WATER_MOVE_EFF ATTR_OXYGEN_BONUS | +0.5 water efficiency and +2 oxygen | 4 | Easy | Planned | Land is where you keep your things.
nether_native | Nether Native | Exploration | Rare | Unlimited | - | No | - | Spend 7 in-game days in the Nether | Tick sampler with dimension check | At home in hell | ATTR_BURNING_TIME DMG_VS_TYPE | -50% burn time and +10% vs nether mobs | 5 | Medium | Planned | The screaming became background noise.
treasure_hunter | Treasure Hunter | Exploration | Rare | Unlimited | - | No | - | Open 50 naturally-generated loot chests | Custom container-open tracker | Better loot rolls | LOOT_LUCK_CONTEXT ATTR_LUCK | +2 effective luck on generated loot | 6 | Hard | Planned | X does not actually mark anything. You check anyway.
void_walker | Void Walker | Exploration | Epic | Unlimited | - | No | - | Enter 10 distinct End Cities | Structure lookup on a tick sampler while in the End - dedupe by structure start position | Ender pearls cost you nothing | CUSTOM ATTR_FALL_DAMAGE_MULT | No pearl teleport damage and -50% fall damage | 7 | Medium | Planned | Edges are a matter of opinion.
cinderhand | Cinderhand | Exploration | Rare | Unlimited | - | Yes | Something came back through the portal with you. | Enter the Nether for the first time | Dimension change event - first entry to the_nether | Your weapons burn without being enchanted | ENCHANT_INTRINSIC | Fire Aspect I on melee attacks | 5 | Medium | Planned | The heat did not stay behind.
farstep | Farstep | Exploration | Epic | Unlimited | - | Yes | Distance stopped being the problem some time ago. | Enter the End for the first time | Dimension change event - first entry to the_end | Throw an ender pearl you do not have | ACTIVE_ABILITY | Conjured ender pearl on use - 5 second cooldown - costs nothing | 7 | Hard | Planned | You left something out there. It answers when you call.
apprentice_smith | Apprentice Smith | Crafting | Common | Unlimited | - | No | - | Craft 100 pieces of armor | Vanilla stat ITEM_CRAFTED over a tag | Armor lasts longer | CUSTOM | -10% armor durability consumption | 2 | Medium | Planned | Cheap plate - patched twice - still holding.
master_smith | Master Smith | Crafting | Rare | Unlimited | - | No | - | Craft 200 tools or weapons | Vanilla stat ITEM_CRAFTED over a tag | Your gear outlives everyone else's | CUSTOM | -20% durability consumption on tools and armor | 6 | Medium | Planned | Measure once. You already know.
enchanter | Enchanter | Crafting | Epic | Unlimited | - | No | - | Enchant 50 items | Vanilla stat over enchanting table interaction | Better enchantment rolls | CUSTOM | +2 effective enchanting levels and -1 lapis cost | 7 | Hard | Planned | The words rearrange themselves for you now.
alchemist | Alchemist | Crafting | Rare | Unlimited | - | No | - | Brew 100 potions | Custom brewing-stand tracker | Potions last longer on you | POTION_DURATION_MULT | +30% duration on beneficial effects | 6 | Medium | Planned | Everything is a dosage question.
grand_alchemist | Grand Alchemist | Crafting | Legendary | Limited | 2 | No | - | Brew every potion type in the game | Custom brewed-type set | SIGNATURE - your brews come out a tier stronger | POTION_AMPLIFIER_BOOST | +1 amplifier on self-brewed potions from a fixed allowlist | 5 exempt | Hard | Planned | You stopped reading the recipes years ago.
haggler | Haggler | Trading | Common | Unlimited | - | No | - | Complete 20 villager trades | Vanilla stat TRADED_WITH_VILLAGER | A small discount everywhere | CUSTOM | -10% trade cost | 2 | Medium | Planned | You always ask. It usually works.
restocker | Restocker | Trading | Uncommon | Unlimited | - | No | - | Complete 100 villager trades | Vanilla stat TRADED_WITH_VILLAGER | Villagers restock sooner | CUSTOM | -25% villager restock time | 3 | Medium | Planned | They work harder when you are watching.
caravan_friend | Caravan Friend | Trading | Uncommon | Unlimited | - | No | - | Trade with 10 different wandering traders | Custom trader-uuid set | Wandering traders find you more often | CUSTOM | Double wandering trader spawn rate near you | 3 | Medium | Planned | The llamas remember you.
master_trader | Master Trader | Trading | Rare | Unlimited | - | No | - | Complete 200 villager trades | Vanilla stat TRADED_WITH_VILLAGER | Villagers like you | CUSTOM | -25% trade cost and faster restocks | 6 | Hard | Planned | Everyone has a price. You found the discount.
harvester | Harvester | Farming | Common | Unlimited | - | No | - | Harvest 1000 mature crops | Vanilla stat BLOCK_MINED over a crop tag | Crops sometimes yield double | ON_MINE_PROC | 10% double crop drop | 3 | Medium | Planned | The field owes you nothing and pays anyway.
beekeeper | Beekeeper | Farming | Common | Unlimited | - | No | - | Harvest 50 honey bottles or honeycomb | Vanilla stat ITEM_USED with a block check | Bees never turn on you | CUSTOM | Bees never become hostile toward you | 2 | Medium | Planned | You explained yourself and they listened.
shepherd | Shepherd | Farming | Uncommon | Unlimited | - | No | - | Breed 100 animals | Vanilla stat ANIMALS_BRED | Animals follow you further and breed faster | ATTR_TEMPT_RANGE CUSTOM | +4 tempt range and -30% breed cooldown | 4 | Medium | Planned | They trust you. Do not think about dinner.
angler | Angler | Farming | Uncommon | Unlimited | - | No | - | Catch 250 fish | Vanilla stat FISH_CAUGHT | Better fishing loot and faster bites | ATTR_LUCK CUSTOM | +2 luck while holding a rod and -25% bite time | 4 | Medium | Planned | Patience with a hook on the end.
bricklayer | Bricklayer | Building | Common | Unlimited | - | No | - | Place 10000 blocks | Vanilla stat BLOCK_PLACED | Slightly longer reach for building | ATTR_INTERACTION_RANGE | +0.5 block interaction range | 2 | Easy | Planned | One more row before dark.
scaffolder | Scaffolder | Building | Uncommon | Unlimited | - | No | - | Place 500 blocks above y=120 | Vanilla stat BLOCK_PLACED with a height check | Safe and fast at height | ATTR_SAFE_FALL_DISTANCE CUSTOM | +3 safe fall distance and +50% scaffolding climb speed | 4 | Medium | Planned | Height stopped being a feeling.
landscaper | Landscaper | Building | Uncommon | Unlimited | - | No | - | Till 500 blocks and dig 5000 | Vanilla stats over hoe and shovel use | Terrain tools move faster and you step up ledges | TOOL_PROFICIENCY ATTR_STEP_HEIGHT | +25% shovel and hoe speed and +0.5 step height | 4 | Medium | Planned | The land had it coming.
architect | Architect | Building | Epic | Unlimited | - | No | - | Place 100000 blocks | Vanilla stat BLOCK_PLACED | Longer reach and faster placement | ATTR_INTERACTION_RANGE | +1.5 block interaction range | 6 | Easy | Planned | You see the finished thing before the first block.
first_light | First Light | Meta | Legendary | Founding | 50 | No | - | Be one of the first 50 players ever to join this world | Server ledger claim on first join | SIGNATURE - golden nameplate and a numbered founder entry in the ledger | ATTR_MAX_HEALTH ATTR_LUCK | +2 max health and +1 luck | 3 exempt | Easy | Planned | Someone had to turn on the lights. Fifty of you were here to see it.
collector | Collector | Meta | Uncommon | Unlimited | - | No | - | Earn 10 titles | Owned title count | SLOT AND BUDGET EXEMPT - raises your equipped power budget | CUSTOM | +2 power budget | 0 exempt | Medium | Proposed | Ten is where a habit starts.
archivist | Archivist | Meta | Epic | Unlimited | - | No | - | Earn 25 titles | Owned title count | SLOT AND BUDGET EXEMPT - raises your equipped power budget | CUSTOM | +4 power budget | 0 exempt | Medium | Proposed | You keep the list. The list keeps you.
chronicler | Chronicler | Meta | Legendary | Unlimited | - | No | - | Earn 50 titles | Owned title count | SLOT AND BUDGET EXEMPT - raises your budget and marks your nameplate | CUSTOM | +6 power budget and a nameplate flourish | 0 exempt | Medium | Proposed | Half the world's deeds have your name on them.
the_unrivaled | The Unrivaled | Meta | Unique | Contested | 1 | No | - | Hold the most wins in agreed player-vs-player duels on the server | Duel ledger - both players opt in to a duel and the server records the winner | SIGNATURE - gold name on the tab list. Transfers the moment someone passes your win count. | CUSTOM ATTR_ATTACK_DAMAGE | Gold tab-list name and +10% damage | 3 exempt | Hard | Proposed | Someone is always counting.
the_generous | The Generous | Social | Rare | Unlimited | - | Yes | Something you gave away is still being counted. | Drop 100 items that another player picks up | Item pickup attribution | Being kind pays | XP_MULT ATTR_LUCK | +25% XP and +1 luck | 5 | Hard | Planned | Nobody told you it counted.
pacifist | Pacifist | Meta | Legendary | Limited | 3 | Yes | Fifteen days is a long time to keep your hands clean. | Reach 15 in-game days having killed no mob or player | Kill stat sum must stay zero | SIGNATURE - hostile mobs are slow to notice you | CUSTOM ATTR_MAX_HEALTH | -40% mob detection range and +8 max health | 4 exempt | Hard | Planned | You just walked past all of it.
the_hollow | The Hollow | Secret | Epic | Unlimited | - | Yes | The respawn screen knows you by name. | Die 100 times | Vanilla stat DEATHS | Death costs less | CUSTOM | Keep 50% of XP on death and respawn with Absorption | 7 | Medium | Planned | You know the way back now.
moonstruck | Moonstruck | Secret | Rare | Unlimited | - | Yes | The moon keeps a ledger of quiet nights. | Sleep through 25 nights without ever sleeping through a thunderstorm | Sleep event with weather check | Stronger at night | ATTR_ATTACK_DAMAGE | +15% damage between dusk and dawn | 6 | Medium | Planned | The moon has opinions about you.
the_drowned_king | The Drowned King | Secret | Unique | Unique | 1 | Yes | The temple has a throne. Its rules are drowning ones. | Kill an Elder Guardian while under Mining Fatigue III and drowning | Compound condition on kill event | SIGNATURE - permanent water breathing. Utility not combat power. | CUSTOM ATTR_WATER_MOVE_EFF | Water breathing and +50% swim speed | 4 exempt | Hard | Planned | The temple has a new tenant.
warden_touched | Warden Touched | Secret | Unique | Unique | 1 | Yes | It let you go. It keeps letting you go. | Escape a Warden after it has fully aggroed on you 10 times | Warden aggro/escape tracker | SIGNATURE - sculk sensors and shriekers never detect you | CUSTOM | Sculk immunity and +15% damage from stealth | 4 exempt | Hard | Planned | It let you go. Nine times you thought that was luck.

## Rarity and Scarcity
Rarity | Hex Color | MC Format | Starter Roll Weight | Power Budget | Typical Unlock Effort | Count in Sheet | UI Treatment
Common | AAAAAA | gray | 50 | 1-4 | Minutes to an hour of normal play | 47 | Plain text
Uncommon | 55FF55 | green | 28 | 3-4 | A full session of focused play | 16 | Plain text
Rare | 55FFFF | aqua | 14 | 5-6 | Several sessions or a boss/structure | 16 | Subtle shimmer on hover
Epic | FF55FF | light_purple | 6 | 7-8 | Long-term grind or a hard challenge | 10 | Animated gradient border
Legendary | FFAA00 | gold | 2 | 9-10 | Server-notable achievement | 7 | Full-card glow + server broadcast on earn
Mythic | FF5555 | red | 0 | 11-13 | Once-per-world class event | 2 | Screen flash + title card + broadcast
Unique | 00AAAA | dark_aqua | 0 | 5 exempt | A one-of-a-kind world event or a closed founder race | 5 | Solid teal nameplate + title card + broadcast + a permanent numbered entry in the server ledger
Scarcity Type | Meaning | Max Holders | On Holder Death | On Holder Inactivity | On Server Reset | Recommended Use
Unlimited | Anyone who meets the condition gets it | Unbounded | Kept | Kept | Kept | Default for 90% of titles
Limited | Only N players on the server may hold it at once | 2-10 | Kept | Kept - NEVER released | Released | Prestige grind titles. An inactive holder keeps the slot forever - see the never-revoked rule below
Unique | Exactly one holder for the life of the world | 1 | Kept | Kept | Released | First-to-do-X achievements
Founding | The first N players ever to meet the condition claim it - then it is closed forever and never reopens | 10-50 - set per title | Kept | Kept - NEVER released | Released | Founder titles and first-N-to-achieve races. Unlike Limited this is not a rotating pool - being early is a historical fact and cannot be taken back
Contested | Unique but transferable - a new claimant takes it from the holder | 1 | Kept | Kept | Released | THE ONLY REVOCABLE SCARCITY TYPE. Lost only when another player beats the holder's score - never on death and never on inactivity. Used by The Unrivaled alone
Note | Starter Roll Weight is the relative chance of that rarity in the free title granted on first join. Weights sum to 100 across Common..Legendary. Mythic and Unique are never rolled - they are only ever earned.
Note | DECIDED - TITLES ARE NEVER REVOKED. Once earned a title is yours permanently - it survives death - inactivity - and dimension change. The sole exception is the Contested type - currently The Unrivaled alone - which passes to whoever beats the holder's score.
Note | DECIDED - Unique IS a rarity - the top of the ladder above Mythic. It marks a title that can never be earned again once claimed. It does not carry a point range like the other tiers - a Unique title is budget-exempt and capped at 5 points of raw stats like every scarce title - so its rarity is expressed as a signature ability and public prestige.
Note | Unique is the one word that appears in BOTH the Rarity column and the Scarcity column and they mean different things. Rarity Unique = irreplaceable - the client paints it dark_aqua and broadcasts it. Scarcity Unique = exactly one holder. A title can be one without the other - Monster Slayer is Rarity Unique with Scarcity Founding because ten players may each claim it once and then it closes forever. Read Scarcity for the holder count and Rarity for the presentation.
Note | DECIDED - Secret is NOT a rarity. It is a Yes/No flag on the Titles sheet that is orthogonal to rarity. A secret title has a normal rarity and normal power - the player just does not know it exists until it fires. 11 titles are currently flagged secret.
Note | Secret titles carry a Hint string on the Titles sheet. The Titles screen shows ??? plus the hint once partial progress is detected - see the UI Spec sheet - so they stay discoverable instead of becoming wiki chores.
Note | Common runs 1-4 points rather than 1-2. Single-mob damage titles sit at 2 and the broad-tag or max-health commons sit at 3-4. Ten commons equipped is roughly 25-30 points - still under the 40 cap by design.
Note | Power Budget is a soft cap. Sum the point costs on the Effect Catalog sheet and keep a title at or under its rarity budget.
Note | DECIDED - a player equips up to 10 titles at once plus every Unique and Limited title they hold. Unique and Limited titles are budget-exempt. See the Balance Model sheet.
Note | DECIDED - equipped titles are capped at a 40-point total budget. Scarce titles are exempt from the budget but capped at 5 points of raw stats each.

## Effect Catalog
Effect Type | Implementation Hook | Attribute ID on 1.20.1 (VERIFY in-game) | Example Magnitude | Point Cost | Difficulty | Notes
ATTR_MAX_HEALTH | AttributeModifier ADDITION | minecraft:generic.max_health | +4.0 (2 hearts) | 4 | Easy | Remove modifier on unequip or players keep the hearts
ATTR_ARMOR | AttributeModifier ADDITION | minecraft:generic.armor | +2.0 | 3 | Easy | Flat armor points - very strong early
ATTR_ARMOR_TOUGHNESS | AttributeModifier ADDITION | minecraft:generic.armor_toughness | +2.0 | 3 | Easy | Reduces high-damage-hit scaling
ATTR_KNOCKBACK_RESIST | AttributeModifier ADDITION | minecraft:generic.knockback_resistance | +0.2 (20%) | 2 | Easy | 1.0 = immune. Keep low
ATTR_ATTACK_DAMAGE | AttributeModifier MULTIPLY_TOTAL | minecraft:generic.attack_damage | +10% | 4 | Easy | Multiplied applies after weapon damage
ATTR_ATTACK_SPEED | AttributeModifier MULTIPLY_TOTAL | minecraft:generic.attack_speed | +10% | 4 | Easy | Big DPS impact - be conservative
ATTR_MOVEMENT_SPEED | AttributeModifier MULTIPLY_TOTAL | minecraft:generic.movement_speed | +5% | 3 | Easy | Above +20% feels broken and breaks some anti-cheat
ATTR_LUCK | AttributeModifier ADDITION | minecraft:generic.luck | +1.0 | 3 | Easy | Only affects loot tables with quality/bonus_rolls - fishing, chests
ATTR_BLOCK_BREAK_SPEED | AttributeModifier MULTIPLY_TOTAL | NOT IN 1.20.1 - use Forge PlayerEvent.BreakSpeed | +15% | 3 | Medium | Global mining speed multiplier
ATTR_MINING_EFFICIENCY | AttributeModifier ADDITION | NOT IN 1.20.1 - fold into the same BreakSpeed hook | +2.0 | 3 | Medium | Behaves like the Efficiency enchant term
ATTR_SUBMERGED_MINING | AttributeModifier ADDITION | NOT IN 1.20.1 - BreakSpeed hook - check isEyeInFluid | +0.5 | 1 | Medium | Removes the underwater mining penalty
ATTR_SNEAKING_SPEED | AttributeModifier MULTIPLY_TOTAL | NOT IN 1.20.1 - no clean hook - CUT for v1 | +30% | 1 | Medium | Quality of life - cheap
ATTR_STEP_HEIGHT | AttributeModifier ADDITION | forge:step_height_addition - Forge-added - VERIFY | +0.5 | 2 | Easy | Walk up full blocks
ATTR_SAFE_FALL_DISTANCE | AttributeModifier ADDITION | NOT IN 1.20.1 - LivingFallEvent - raise the threshold | +3.0 | 2 | Medium | Fall damage starts later
ATTR_FALL_DAMAGE_MULT | AttributeModifier MULTIPLY_TOTAL | NOT IN 1.20.1 - LivingFallEvent damageMultiplier | -25% | 2 | Medium | Negative value = less damage
ATTR_OXYGEN_BONUS | AttributeModifier ADDITION | NOT IN 1.20.1 - tick hook on air supply | +2.0 | 2 | Medium | Longer breath underwater
ATTR_BURNING_TIME | AttributeModifier MULTIPLY_TOTAL | NOT IN 1.20.1 - tick hook trimming remaining fire ticks | -50% | 2 | Medium | Shorter time on fire
ATTR_EXPLOSION_KB_RESIST | AttributeModifier ADDITION | NOT IN 1.20.1 - no clean hook - CUT for v1 | +0.5 | 2 | Medium | Creeper/TNT knockback only - not damage
ATTR_INTERACTION_RANGE | AttributeModifier ADDITION | forge:block_reach / forge:entity_reach - Forge-added - VERIFY | +1.0 | 3 | Easy | Very noticeable in PvP - gate behind high rarity
ATTR_JUMP_STRENGTH | AttributeModifier MULTIPLY_TOTAL | NOT IN 1.20.1 for players - horse only - use LivingJumpEvent | +10% | 3 | Medium | Pair with safe_fall_distance or players die to it
ATTR_MAX_ABSORPTION | AttributeModifier ADDITION | minecraft:generic.max_absorption - VERIFY it exists on 1.20.1 | +4.0 | 4 | Medium | Needs a refill source or it does nothing
ATTR_WATER_MOVE_EFF | AttributeModifier ADDITION | forge:swim_speed - Forge-added - VERIFY | +0.5 | 2 | Easy | Depth Strider equivalent
ATTR_GRAVITY | AttributeModifier MULTIPLY_TOTAL | forge:entity_gravity - Forge-added - VERIFY | -10% | 3 | Medium | Feels odd - test heavily before shipping
DMG_VS_TYPE | Damage event - check target entity type tag | n/a | +15% vs undead | 4 | Medium | Forge LivingHurtEvent (pre-armor) or LivingDamageEvent (post-armor). Use entity type TAGS not hardcoded types
DMG_RESIST_FROM_TYPE | Damage event - check source entity type | n/a | -20% from creepers | 4 | Medium | Also match DamageSource types for explosion/fire/projectile
DMG_VS_DAMAGE_SOURCE | Damage event - check DamageSource tag | n/a | -30% explosion damage | 3 | Medium | Cleaner than entity checks for environmental damage
TOOL_TIER_HAND | Break-speed event + correct-tool-for-drops event | n/a | Bare hand counts as stone tier | 5 | Hard | TWO hooks. Speed alone still drops nothing - you must also override the drop check
TOOL_PROFICIENCY | Break-speed event scoped to a tool tag | n/a | +25% speed with axes | 3 | Medium | Scope by item tag so modded tools benefit too
POTION_DURATION_MULT | Effect-added event - rebuild the MobEffectInstance | n/a | +25% duration | 4 | Medium | Only extend beneficial effects. Watch for infinite re-application loops
POTION_AMPLIFIER_BOOST | Effect-added event | n/a | +1 amplifier on self-brewed potions | 6 | Hard | Amplifier jumps are huge. Restrict to specific effects
XP_MULT | XP pickup / drop event | n/a | +20% XP | 2 | Easy | Popular and safe
PASSIVE_EFFECT | Re-apply a hidden MobEffectInstance every 40 ticks | n/a | Night Vision while below y=0 | 3 | Medium | Use ambient+hidden particles or it looks terrible
ON_KILL_PROC | Death event | n/a | 10% chance to restore 1 heart on kill | 4 | Medium | Add an internal cooldown
ON_HURT_PROC | Damage event | n/a | Below 30% HP gain Strength I for 5s | 5 | Medium | Cooldown mandatory
ON_MINE_PROC | Block break event | n/a | 3% chance to double ore drops | 5 | Medium | Respect Silk Touch and fortune. Do not double-fire on multi-block breaks
LOOT_LUCK_CONTEXT | Loot context modifier | n/a | +1 effective luck on chest loot | 4 | Hard | Requires a global loot modifier
ENCHANT_INTRINSIC | Attack event - apply an enchantment's effect as if the held weapon carried it | n/a | Fire Aspect I on any melee weapon | 4 | Medium | Apply the EFFECT - never write the enchantment onto the item or it survives being dropped or traded. Do not stack with a real Fire Aspect on the same weapon - take the higher level
ACTIVE_ABILITY | Keybind or use event plus a per-player server-side cooldown | n/a | Throw a conjured ender pearl on a 5 second cooldown | 6 | Hard | THE FIRST ACTIVATED ABILITY IN THE MOD. Needs a keybind - a cooldown readout on the HUD - and cooldown validation on the server. Never trust a client-reported cooldown
CUSTOM | Bespoke code | n/a | Varies | Varies | Hard | Reserve for Legendary/Mythic only - each one is a maintenance burden
IMPORTANT | Attribute IDs are now written for 1.20.1 - note the generic. prefix that 1.21 later removed - and Operation is the old ADDITION / MULTIPLY_BASE / MULTIPLY_TOTAL enum. Print the full attribute registry in-game as the Phase 0 task says and correct anything marked VERIFY.
IMPORTANT | On 1.20.1 a modifier is keyed by UUID - not by ResourceLocation. Store a ResourceLocation-shaped id in the title JSON and derive the UUID from it with UUID.nameUUIDFromBytes so the content files survive the port untouched. Reusing one id across two titles makes the second silently overwrite the first.
IMPORTANT | Always remove modifiers on unequip AND on player logout-save. Orphaned max_health modifiers are the classic way this kind of mod corrupts a save.
IMPORTANT | COST OF THE 1.20.1 DECISION - 12 of the 23 ATTR_ effects below have no vanilla attribute on 1.20.1. They were all added in 1.20.5 / 1.21. Each is now an event hook instead of a free attribute modifier - more code - more to test - and more to delete at port time when the real attribute finally exists.
IMPORTANT | Re-cost the affected effects on the Balance Model sheet. Point costs were set assuming these were cheap attribute modifiers. An event-hook implementation does not change how strong the effect is - but it does change whether it is worth building for v1. ATTR_SNEAKING_SPEED and ATTR_EXPLOSION_KB_RESIST are the two to cut.

## Progress Triggers
Trigger Family | Best Source | Why | Example Call or Hook | Perf Cost | Exploit Risk | Mitigation
Blocks mined by type | Vanilla statistics | Already tracked per block per player and already saved to disk. Free. | player.getStats().getValue(Stats.BLOCK_MINED, Blocks.STONE) | None | Place-and-break loops inflate counts | Require net-new blocks or check the block was not player-placed. On 1.20.1 there are no chunk attachments - flag player-placed blocks in a chunk capability or a SavedData set of your own
Mobs killed by type | Vanilla statistics | Tracked per entity type per player | Stats.ENTITY_KILLED with an EntityType | None | Mob farms make kill counts trivial | Raise thresholds or require kills without a farm nearby. Honestly - just accept farms for common titles
Items crafted | Vanilla statistics | Tracked per item | Stats.ITEM_CRAFTED | None | Craft-uncraft loops | Use items that cannot be uncrafted or count distinct types
Deaths / damage taken / distance | Vanilla statistics | All tracked already | Stats.DEATHS Stats.DAMAGE_TAKEN Stats.WALK_ONE_CM | None | Low | -
Playtime and time since death | Vanilla statistics | Both exist | Stats.PLAY_TIME and Stats.TIME_SINCE_DEATH | None | AFK farms inflate playtime | Use TIME_SINCE_DEATH which is what survival titles actually want
Complex compound conditions | Vanilla advancement criteria | Advancements are already a JSON predicate engine with entity/damage/location/item predicates. Do not rebuild this. | Custom advancement with a title id in its reward or a listener on AdvancementEvent | None | Advancement command grants | Disable /advancement for non-ops or listen for legitimate grants only
Damage dealt or taken with conditions | Event hook | Stats cannot express "while below 4 hearts" | Forge LivingHurtEvent (pre-armor) or LivingDamageEvent (post-armor) | Low | Low | Cache the equipped-title effect list per player - do not stream over titles every hit
Block break speed and tool tier | Event hook | Needs two separate hooks | PlayerEvent.BreakSpeed AND PlayerEvent.HarvestCheck (or the 26.x equivalents) | Low | Low | Speed without the harvest check means you mine fast and get nothing
Biome / dimension presence | Tick sampler | No vanilla stat for this | Every 100 ticks on the server player list | Low if sampled | AFK in a biome | Fine - that is the intended cost
Standing in armor / holding an item | Tick sampler | No vanilla stat | Every 40-100 ticks | Low if sampled | Low | Never do this every tick for every player
Chest opens / container loot | Event hook | Needs the loot table origin | Container open event + loot table id check | Low | Re-opening the same chest | Store opened-chest positions in a bounded LRU per player
Fishing / breeding / trading | Vanilla statistics | Stats.FISH_CAUGHT ANIMALS_BRED TRADED_WITH_VILLAGER | Free | None | Automated farms | Accept it or add a manual-action check
Server-first claims | Server SavedData | The ledger is the source of truth | On the server tick that the condition passes - claim under the ledger before granting | None | Race between two players in the same tick | The server tick is single-threaded. Check-then-claim in one synchronous block and it is genuinely safe
EVALUATION MODEL | Do NOT re-evaluate every title for every player every tick.
Recommended | Titles register the trigger families they care about. When a matching event fires for a player only that player's candidate titles are re-checked. Plus one low-frequency sweep every 200 ticks for tick-sampler titles.
Recommended | Once a title is earned it is removed from that player's candidate set permanently. The check cost drops as players progress.

## UI Spec
Element | Description | Detail | Priority | Status
Open method | Keybind (default K) plus a /titles command | Command matters for servers where keybinds conflict | P0 | Planned
Layout | Left: scrollable grid of title cards. Right: detail panel for the selected title. | Grid of 4 columns fits a standard 176px-wide GUI poorly - build a wider custom screen around 256x220 | P0 | Planned
Title card | Name in rarity color plus a small rarity pip and an equipped indicator | Locked cards are grayed. Secret unearned cards show ??? only | P0 | Planned
Detail panel | Full name - rarity - scarcity - flavor text - bulleted effect list with exact numbers | Show real numbers not vague words. LitRPG players want the stat block | P0 | Planned
Effect list rendering | Generated from the effect data not hand-written strings | One display formatter per effect type. Otherwise your tooltips drift from the code | P0 | Planned
Equip slots | 10 slots in two rows of 5. Drag or click to equip. | Equipping is a server round trip - never apply optimistically on the client | P0 | Planned
Budget meter | Prominent "31 / 40" readout beside the slots that updates as you hover a candidate title | Show the projected total on hover before the player commits. Over-budget candidates render red and refuse the equip. | P0 | Planned
Scarce title shelf | Separate always-on row below the 10 slots for Unique and Limited titles | Visually distinct - these are not equipped and cannot be unequipped. Label it so nobody thinks they are wasting slots. | P0 | Planned
Per-attribute cap feedback | When a cap is hit show the contributing effect struck through with "capped" | Otherwise players stack two damage titles and quietly get nothing for the second | P1 | Planned
Progress bars | For unearned non-secret titles show current/required | Requires syncing progress counters to the client - throttle to once a second while the screen is open | P1 | Planned
Filters | Tabs or dropdown by category plus toggles for Earned / Unearned / Secret | Becomes essential past about 30 titles | P1 | Planned
Search box | Filter by name and effect keyword | Cheap to add and very appreciated | P1 | Planned
Sort | By rarity - category - recently earned | P2 | P2 | Planned
Scarcity display | For Limited and Founding titles show "2 of 3 claimed" and who holds them | Needs a synced server ledger snapshot. Big driver of the prestige feeling. Suppressed for secret titles until first claim - see the row below | P1 | Planned
Secret scarce titles | DECIDED - a secret title with a limited number of holders stays fully hidden until the FIRST player claims it. That claim broadcasts server-wide and permanently reveals the title - name - hint - holder roster and remaining slots - to everyone. The remaining slots then become a public race. | Resolves the collision between "secret shows ??? " and "scarce shows 2 of 3 claimed" - you cannot do both before the reveal or the counter leaks the secret. Reveal is a one-way flag on the ledger entry - not per-player - so everyone sees the same state. Currently applies to Monster Slayer (Founding 10) and Pacifist (Limited 3). | P1 | Planned
Earn notification | Toast plus a sound plus an optional server broadcast for Legendary and above | Reuse the vanilla advancement toast style so it feels native. For a secret scarce title the FIRST claim always broadcasts regardless of rarity - that broadcast is what performs the reveal | P0 | Planned
Secret hint system | Optional per-title hint string revealed after partial progress | Keeps secret titles discoverable rather than wiki-only | P2 | Planned
HUD element | Optional small equipped-title display near the hotbar | Client config for position and visibility | P2 | Planned
Nameplate / chat prefix | Show the primary equipped title above the player and before chat messages | Very popular in multiplayer. Make it toggleable - some servers hate it | P2 | Planned
Accessibility | Never encode meaning in color alone - the rarity pip shape and the text label carry it too | Also respect the vanilla GUI scale and narrator | P1 | Planned
Sync protocol | Server sends the full title state on join and deltas on change. Client never computes eligibility. | Payload stays small if you send ids not full definitions - the client already has the registry from the datapack sync | P0 | Planned

## Design Decisions
Topic | The Question | Option A | Option B | Recommendation | Why | Knock-on Effects
Equipped vs owned | Are all earned titles always active? | All earned titles always active | Collect many - equip a limited set | DECIDED - 10 equip slots | Equip slots turn titles into build choices and make every new title interesting forever. 10 is generous enough to feel like a real character sheet. | Needs equip UI - needs modifier add/remove on swap - see the Balance Model sheet for the cap that makes 10 slots safe
What actually limits power | If there are 10 slots what stops a player equipping 10 Legendaries? | Slot count alone | A point budget across equipped titles | DECIDED - 40-point budget cap on top of the 10 slots | 10 Legendary titles is roughly 95 points - about +100% damage and +20 hearts. Slots are the shape of the build. The budget is the actual limiter. Early players are never constrained by it because they do not own enough titles yet - it only bites exactly when it needs to. | Equip handler must reject over-budget equips server-side. UI shows "31 / 40" live
Scarce title stacking | Do Unique and Limited titles consume a slot or budget? | Yes | No - they stack on top | DECIDED - budget-exempt and slot-exempt | Player decision and a good one. Makes scarce titles feel genuinely special rather than a slot tax you resent. | Only safe because of the scarce power ceiling below - do not ship one without the other
Scarce title power ceiling | How strong can a budget-exempt title be? | As strong as its rarity suggests | Capped low with a signature power instead | DECIDED - max 5 points of raw stats each | Without this the exemption breaks the whole model. A veteran holding 9 scarce titles would carry ~90 free points and the 40-point budget would be decoration. Scarce titles earn their status through a signature ability and public prestige - not big numbers. | All 9 scarce titles in the Titles sheet were re-specced to this rule
Per-attribute caps | Can a player dump the whole budget into one stat? | Yes | No - hard caps per attribute | DECIDED - hard caps - see Balance Model | Second safety net. Clamps the final summed total including scarce contributions. Stacked damage resistances approaching immunity is the classic way this genre breaks. | Clamp at modifier-application time not at equip time
Single player parity | How does scarcity work with one player? | Disable scarce titles in SP | Same code path - the ledger just has one player | DECIDED - same code path | SP runs an integrated server so server-authoritative logic works identically with zero special casing. Unique titles become ordinary achievements - which is fine. Nothing to build and nothing to test twice. | Write everything server-side and SP is free. Add a config toggle to hide scarcity UI in SP if it reads oddly
Starter title | What does the random first-join title do? | Fully random from all titles | Random from the Common and Uncommon pool only | Weighted roll over Common..Legendary using the rarity weights | Small chance of something great is the hook. Rolling a Mythic on join devalues the whole ladder | Must exclude Unique/Limited titles from the roll or first-joiners hoard the scarce ones
Limited title release | What happens when a Limited holder stops playing? | Held forever | Released after N days offline | DECIDED - held forever. Nothing is ever released | Player decision - titles are never revoked. Losing a 150-day deathless grind because you took a month off is exactly the feel-bad this sheet warns about elsewhere. The cost is that latecomers on an old server cannot chase a filled Limited title - accepted. Raise the holder cap in the server config if a title fills up too fast | No last-seen sweep needed at all - the ledger becomes append-only which is simpler and crash-safer
Contested titles | Should any title be stealable? | No | Yes for a small set | Yes but only 1-2 Mythic ones | Rivalry is fun in small doses. Broadly applied it makes the mod feel punishing | Needs a transfer event - a broadcast - and a grace period so it does not ping-pong
Losing titles | Can you lose an earned title? | Never | On failing the condition | DECIDED - NEVER - for every scarcity type | Revocable titles feel awful and create save-scumming. A title is a record of something you did - the deed does not stop having happened | Sole exception is the Contested type - currently The Unrivaled alone - where being overtaken IS the mechanic. Everything else survives death and inactivity forever
Balance ceiling | How strong is a fully-kitted player? | Uncapped | Budget-capped | Cap total equipped power budget - see the Rarity sheet | Without a cap you will not notice the mod is broken until someone posts a video | Enforce in code - refuse to equip past the cap - do not rely on discipline
Multiplayer fairness | Do scarce titles create toxicity? | Ignore it | Design against it | Design against it | Limited and Unique titles are the best idea in this mod and the biggest risk. Keep them prestige-flavored rather than raw-power-defining | Scarce titles should be roughly equal in power to a common title of the same rarity - the scarcity IS the reward
Secret titles | How do players find them? | Pure wiki knowledge | In-game hints | Hint after partial progress | Pure secrets get datamined day one and then they are just wiki chores. Hints keep discovery alive | Needs a partial-progress notion for compound conditions
Data-driven vs hardcoded | Where do titles live? | Java constants | Datapack JSON | Datapack JSON with a codec | Costs you two days up front and saves you months. Also lets modpack authors rebalance without forking | Effects need a registry of effect types with codecs. This is the single best architectural investment here
Effect types | How many bespoke effects? | Every title is custom code | Composable effect primitives | Primitives - CUSTOM only for Legendary+ | 60 bespoke effects is 60 things that break every game update. Attribute-based effects survive updates almost for free | The Effect Catalog sheet is your primitive list
Progress tracking | Build a custom stat system? | Yes | Reuse vanilla stats and advancements | Reuse both | Vanilla already tracks blocks mined per block and mobs killed per type per player and persists it. Advancements are already a JSON condition engine. Reusing them removes most of your backend | Custom counters only for what vanilla genuinely cannot express
Death handling | Do titles survive death? | Yes | No | Yes - always | Losing a grind to a creeper would end the mod's goodwill instantly | On Forge you must copy the record yourself in PlayerEvent.Clone - there is no copyOnDeath flag until the port. Test it - this is a classic silent bug
Creative and cheats | Can you earn titles in creative? | Yes | No | No by default - configurable | Otherwise every title is a five-minute creative session | Also gate on gamemode changes mid-progress
Compat with other mods | Modded blocks and mobs count? | No | Yes via tags | Yes via tags | Writing conditions against minecraft:stone instead of the stone tag means the mod is dead in any modpack | Use tags everywhere in conditions and in damage-vs-type checks
Command surface | What admin tools? | None | Full grant/revoke/list | Full - plus a ledger inspection command | Server admins will need to fix things and you will need it for testing on day one | /titles grant / revoke / list / ledger / reset - all op-gated
Target version and loader | Which Minecraft version and loader do we build for first? | Latest - 26.x on NeoForge | 1.20.1 on Forge | DECIDED - 1.20.1 on Forge 47.x | Every mod we want to integrate with ships Forge 1.20.1 only. Integration is the single requirement that cannot be solved in code - everything else can. 1.20.1 also still has one of the two largest modded player bases so this is not an exile to a dead version. | Overrides the earlier NeoForge-only decision. Costs us Java 17 - obfuscated mappings - Capabilities instead of Attachments - and ForgeGradle. The eventual port crosses a loader change and five years of API churn at once.
Porting strategy | How do we get from 1.20.1 to modern? | A branch per intermediate version | One jump from a finished 1.20.1 to current stable | DECIDED - one jump - skip every intermediate | Intermediate versions have no meaningful player base. Porting five times multiplies the worst breaking-change era in modding history by five. Port once - with a shipped and playtested mod in hand rather than a half-built one. | Two long-lived branches only. Cherry-pick forward from 1.20.1. Do NOT keep a shared main that merges into both - with this much API divergence that is a permanent merge-conflict tax.
Forward compat - serialization | How do we make the eventual port cheap? | Hand-written NBT read and write | Codecs for everything serialized | DECIDED - codecs everywhere - never hand-write NBT | Codecs exist in 1.20.1 and survive the whole span to 26.x essentially unchanged. Highest-value forward-compat rule on this sheet and it costs nothing to follow from day one. | Applies to title JSON - player data - packets and the scarcity ledger alike. No exceptions.
Forward compat - player data | Where does player state actually live? | Inside the Capability class | In a plain record that the Capability merely holds | DECIDED - codec-backed record - capability is a thin holder | Forge Capabilities do not exist on NeoForge 26.x - Data Attachments replace them outright. If the state lives in a POJO the port swaps the holder and the data is untouched. If the state lives in the capability the port is a rewrite. | Same rule for the per-world ledger. SavedData does survive the port but keep its payload a codec-backed record regardless.
Forward compat - networking | What shape are packets? | Whatever SimpleChannel wants | Records with a codec plus a handle(player) method | DECIDED - packet records with codecs | 1.20.2 rewrote networking wholesale. SimpleChannel registration is roughly ten lines of glue we throw away - the payload-based system on 26.x wants nearly the same record shape underneath it. | Keep every bit of packet handling logic out of the registration glue. The glue should do nothing but wire things up.
Forward compat - attribute ids | How do we key attribute modifiers? | A hardcoded UUID per title | A ResourceLocation-shaped id in the title JSON | DECIDED - id in JSON - derive the 1.20.1 UUID from it | 1.20.1 keys attribute modifiers by UUID - modern versions key them by ResourceLocation. Derive the UUID with UUID.nameUUIDFromBytes over the id string and the content files never need touching at port time. | Every title JSON carries a stable modifier id. The derivation is one small utility method that gets deleted at the port.
Forward compat - item data | Do we ever touch item NBT? | Where convenient | Never | DECIDED - never touch item NBT | 1.20.5 replaced item NBT with data components and that is the nastiest single migration in the range. This mod is player-data-driven so it may never need item data at all. Stay that way on purpose rather than by accident. | If a title effect ever appears to need item NBT - find another route or raise it here as a decision before writing it.
Forge API surface | How much Forge do we let into the codebase? | Use it freely - it is our loader | Confine it behind a small platform layer | DECIDED - confine it - five or six interfaces | Forge to NeoForge renames every package - reshapes the event bus - and deletes Capabilities. Every direct Forge call is a port cost. Every call behind an interface is one adapter rewrite instead of hundreds of scattered edits. | Registration - networking - persistence - events - attributes - screen glue. Stop there. Do not build an abstraction for something with exactly one implementation and no second one on the horizon.
Integration dependencies | How do we depend on the Forge mods we integrate with? | Hard dependency | Soft dependency with one isolated compat class each | DECIDED - soft dependencies behind mod-loaded guards | A hard dependency means our mod refuses to load without theirs and breaks every time they update. Isolated compat classes also let the port drop any integration whose mod never reached 26.x without touching core code. | Core must load and play correctly with every integration absent. Test that case explicitly - it is the common one for most users.

## Roadmap
Phase | Milestone | Task | Deliverable | Depends On | Est. Effort | Priority | Status
0 - Setup | Dev environment | Generate a Forge 47.x / 1.20.1 project with ForgeGradle 6 on JDK 17 with Parchment mappings and confirm runClient launches | Empty mod loads in game | - | 2h | P0 | Not started
0 - Setup | Dev environment | Print the full attribute and stat registries to a file in-game | Verified list of real attribute IDs for 1.20.1 | Project runs | 1h | P0 | Not started
0 - Setup | Repo hygiene | git init - .gitignore - LICENSE - README - mod metadata | Clean repo | - | 1h | P0 | Not started
0 - Setup | Integration survey | Pin the exact mod list - 1.20.1 Forge versions - Maven coordinates - and whether each publishes a real API or needs reflection | A dependency block that actually resolves in Gradle | - | 3h | P0 | Not started
1 - Core | Platform layer | Define the five or six interfaces that confine the Forge API - registration - networking - persistence - events - attributes - screen glue | No Forge import outside an adapter class | Setup | 1d | P0 | Not started
1 - Core | Title registry | Codec-backed Title record and a datapack registry under data/titles/title/ | Titles load from JSON and log on startup | Setup | 1d | P0 | Not started
1 - Core | Effect system | TitleEffect interface + registry + codecs. Implement the ATTR_ family first. | Attribute effects apply and remove correctly | Title registry | 2d | P0 | Not started
1 - Core | Player data | Forge Capability holding a codec-backed record - earned ids - equipped ids - progress counters. Copy it in PlayerEvent.Clone. | Survives death - dimension change - relog | Platform layer | 1d | P0 | Not started
1 - Core | Grant pipeline | grantTitle() - dedupe - fire an event - toast the player | Titles can be granted by command | Player data | 4h | P0 | Not started
1 - Core | Commands | /titles grant revoke list for testing | Testable without playing | Grant pipeline | 3h | P0 | Not started
2 - Progression | Vanilla stat conditions | Condition types reading Stats.BLOCK_MINED / ENTITY_KILLED / etc from JSON | Stone Breaker and Undead Bane earn themselves | Title registry | 2d | P0 | Not started
2 - Progression | Event conditions | Damage - break - kill event listeners feeding candidate re-checks | Conditional titles work | Stat conditions | 2d | P0 | Not started
2 - Progression | Tick sampler | 200-tick sweep for presence and equipment conditions | Biome and dimension titles work | Event conditions | 1d | P1 | Not started
2 - Progression | Candidate set optimisation | Per-player candidate sets that shrink as titles are earned | No measurable TPS cost with 20 players | Event conditions | 1d | P1 | Not started
3 - UI | Network layer | Sync packets - full state on join and deltas on change | Client mirrors server state | Player data | 1d | P0 | Not started
1 - Core | Equip model | 10 slots + 40-point budget cap enforced server-side in the equip handler | Over-budget equips are rejected with a message | Effect system | 1d | P0 | Not started
1 - Core | Per-attribute caps | Clamp summed attribute totals at application time across equipped AND scarce titles | No single stat can run away | Equip model | 4h | P0 | Not started
3 - UI | Titles screen | Grid - detail panel - 10 equip slots - scarce shelf - keybind | Playable core loop | Network layer | 3d | P0 | Not started
3 - UI | Budget meter | Live "31 / 40" readout with hover projection and red over-budget candidates | Players can optimise their build | Titles screen | 4h | P0 | Not started
3 - UI | Effect formatter | Auto-generated human-readable effect lines per effect type | Tooltips cannot drift from behaviour | Effect system | 4h | P0 | Not started
3 - UI | Earn toast | Toast - sound - broadcast for Legendary+ | It feels good to earn one | Grant pipeline | 4h | P0 | Not started
4 - Scarcity | Server ledger | SavedData tracking Limited and Unique claims plus last-seen timestamps | Ledger persists across restarts | Grant pipeline | 1d | P1 | Not started
4 - Scarcity | Claim logic | Synchronous check-then-claim on the server tick | No double-grants under race | Server ledger | 4h | P1 | Not started
4 - Scarcity | Release sweep | Daily sweep releasing titles from long-inactive holders | Latecomers can chase Limited titles | Server ledger | 4h | P1 | Not started
4 - Scarcity | Ledger UI | Show "2 of 3 claimed" and holder names in the screen | Prestige is visible | Titles screen + ledger | 4h | P1 | Not started
5 - Content | Starter roll | Weighted rarity roll on first join excluding scarce titles | Every new player starts with a title | Grant pipeline | 3h | P0 | Not started
5 - Content | Ship 12 titles | Write the JSON for the v1 title set - one per effect family | Playable vertical slice | Everything in 1-3 | 1d | P0 | Not started
5 - Content | Balance pass | Playtest and tune magnitudes against the power budget | Numbers that survive contact with players | 12 titles | Ongoing | P1 | Not started
5 - Content | Expand to 40+ | Fill out the Titles sheet as JSON | Full content set | Balance pass | 3d | P2 | Not started
6 - Polish | Hard hooks | TOOL_TIER_HAND - break speed plus harvest check | Stone Breaker actually drops blocks | Effect system | 1d | P1 | Not started
6 - Polish | Secret hints | Partial-progress hint reveal | Secrets stay discoverable | Titles screen | 1d | P2 | Not started
6 - Polish | Config | Server balance config and client HUD config | Server owners can tune without forking | Core done | 4h | P1 | Not started
6 - Polish | HUD and nameplate | Optional equipped-title display and chat prefix | Multiplayer flavour | Titles screen | 1d | P2 | Not started
6 - Polish | Mod integrations | One isolated compat class per integration target - each behind a mod-loaded guard | Integrations work when present - mod works standalone when absent | Integration survey + core done | 2d | P1 | Not started
7 - Release | Single player smoke test | Full playthrough in SP - verify scarce titles claim correctly against a one-player ledger | SP parity confirmed | Content done | 2h | P0 | Not started
7 - Release | Dedicated server test | Two clients on a dedicated server - verify sync - contested claims - ledger persistence across restart | MP parity confirmed | Content done | 4h | P0 | Not started
7 - Release | Compat pass | Verify every condition uses tags not hardcoded ids | Works in modpacks | Content done | 4h | P1 | Not started
7 - Release | Docs | README - title list page - datapack authoring guide | Users and pack authors can use it | Content done | 4h | P1 | Not started
7 - Release | Publish | Modrinth and CurseForge listing - screenshots - changelog | v1.0.0 released | All P0 and P1 | 4h | P1 | Not started
8 - Port | Port target | Pick the current STABLE Minecraft and NeoForge version at port time. Do not decide it now and do not accept a beta. | A confirmed stable target | 1.20.1 v1 shipped | 1h | P2 | Not started
8 - Port | Integration triage | Check which integration targets ever reached the new version. Drop the compat classes for those that did not. | Only live integrations ship | Port target | 3h | P2 | Not started
8 - Port | Branch setup | Branch from 1.20.1 - no shared main - cherry-pick forward only | Two long-lived branches | Port target | 1h | P2 | Not started
8 - Port | Toolchain | ModDevGradle - the JDK for that version line - unobfuscated mappings - no Parchment needed | runClient launches on the new version | Branch setup | 4h | P2 | Not started
8 - Port | Platform adapters | Rewrite ONLY the platform layer implementations for NeoForge. Core logic should compile untouched against them. | Core compiles unchanged | Toolchain | 3d | P2 | Not started
8 - Port | Capability to attachment | Move the player data record out of the Forge Capability into a NeoForge Data Attachment with copyOnDeath set | Player data survives death and relog on the new version | Platform adapters | 4h | P2 | Not started
8 - Port | Attribute registry recheck | Re-print the attribute registry and fix every id renamed or removed since 1.20.1. Swap derived UUIDs for ResourceLocation modifier ids. | Every ATTR_ effect resolves | Platform adapters | 4h | P2 | Not started
8 - Port | Screen rewrite | Re-fit the titles screen to the target version widget and rendering APIs | Titles screen usable on the new version | Platform adapters | 2d | P2 | Not started
8 - Port | Parity test | Re-run the whole Phase 7 test list on the ported branch | New version at parity with 1.20.1 v1 | Everything in 8 | 4h | P2 | Not started

## Open Questions
# | Question | Why It Matters | Options | Your Answer
1 | How many equip slots and can that number grow? | Defines the entire balance model | 3 fixed / start at 1 and unlock more / scales with total titles earned | ANSWERED - 10 slots - fixed. Unique and Limited titles stack on top of the 10 and are budget-exempt.
2 | Single player or multiplayer first? | Limited and Unique titles are meaningless in single player. Half the mod's identity depends on this | SP-first with scarcity disabled / MP-first / both with a config toggle | ANSWERED - multiplayer-first but single player must work just as smoothly. Same code path - the integrated server makes this free.
7 | NeoForge only or both loaders? | Doubling loaders early roughly doubles the work | NeoForge only / Fabric only / both | ANSWERED - REVISED - Forge 47.x on 1.20.1 because every integration target is Forge-only. NeoForge after the port to 26.x. Still exactly one loader at a time - never two at once.
3 | Should titles be visible to other players? | Drives whether this is a personal RPG sheet or a social status system. Given the multiplayer-first answer this now matters a lot more | Private / nameplate + chat prefix / opt-in
4 | Do you want a title level or prestige system later? | Changes the data model now - retrofitting levels is painful | Flat titles / titles level up with continued progress
5 | What is the target playstyle - vanilla-plus or full RPG overhaul? | Decides magnitude ranges. The 40-point budget assumes vanilla-plus. An overhaul would roughly double every number | Vanilla-plus / overhaul
6 | Should title effects work in PvP? | Uncapped PvP scaling will get the mod banned from servers. With 10 slots this is now a bigger deal than it was at 3 | Full effect / reduced in PvP / config toggle
8 | Any conflict with existing mods in this space? | Worth 20 minutes on Modrinth before naming it | Check "titles" "ranks" "prestige" on Modrinth
9 | Do titles interact with each other? | Set bonuses and synergies are a great hook. With 10 slots there is real room for them now | None / synergy pairs / full set bonuses
10 | Server-wide or per-world scarcity on a multi-world server? | Affects where the SavedData lives | Per-world / global via a shared file
11 | What is the mod's actual name? | Everything downstream uses the mod id | -
12 | Do you want an achievement-style completion reward? | "Earn 25 titles" as a meta-title is a strong long-term hook | Yes as meta-titles / no
13 | Should the 40-point budget be flat or grow with progression? | Flat means late players choose between titles forever. Growing means the cap is a progression track of its own | Flat 40 / grows from 10 to 40 as you earn titles
15 | Do we build a consensual duel system? | The Unrivaled now depends on it - the title has no unlock condition without a duel ledger. It is a whole subsystem - challenge and accept - win detection - a persistent win counter - and rules for forfeits - disconnects and ties. Nothing else in the mod needs PvP infrastructure | Full duel system with challenge/accept / piggyback on an existing PvP mod / drop the duel idea and give The Unrivaled a different contested condition
14 | Target 26.1 stable or 26.2 beta? | NeoForge has no stable 26.2 release yet - only 26.2.0.41-beta. 26.1 is stable at 26.1.2.93 | 26.1 stable / 26.2 beta | OBSOLETE - superseded by the 1.20.1 decision. Re-ask at port time and take whatever is stable then. Do not pin a version now.
16 | Which mods exactly are we integrating with? | Nothing downstream can be pinned until this list exists. It decides the Gradle dependencies - the API surface we compile against - and how much of Phase 6 survives the port | List each mod with its 1.20.1 Forge version and whether it exposes a real API or needs reflection
17 | Do any integration targets already have a 26.x version? | If most do the port gets far more valuable. If none do then the ported build serves a different audience entirely and the integrations become dead weight | Check each one on Modrinth and CurseForge before committing to the port
18 | Does any integration need more than a soft dependency? | A mod we genuinely cannot function without changes the whole compat story and would make the port hostage to their update schedule | All soft / one is effectively required

## Balance Model
Rule | Value | Rationale
Equip slots | 10 | Player decision. Enough room for a real build identity.
Budget cap on equipped titles | 40 points - server configurable | Slots alone are not a limiter. 10 Legendary titles would be roughly 95 points which is about +100% damage and +20 hearts. The budget is what actually holds the mod together.
Do scarce titles use budget? | No - Unique - Limited and Contested titles are budget-exempt and stack on top of the 10 | Player decision. Makes them feel genuinely special rather than a slot tax.
Scarce title power ceiling | Max 5 points of raw stats each regardless of rarity | THIS IS THE RULE THAT MAKES BUDGET-EXEMPT SAFE. A scarce title earns its rarity through a signature power and public prestige - not big numbers. Otherwise a veteran holding 9 scarce titles has ~90 free points and the budget cap becomes meaningless.
Scarce title signature power | One memorable non-stat ability - utility - cosmetic or situational | Fall immunity - water breathing - sculk invisibility - a revive. Impressive to have and to watch. Not a raw DPS increase.
DELIBERATE EXCEPTION | The Immortal's revive is on a 1 in-game day cooldown - roughly one free totem per 20 minutes of play | Player decision - accepted as knowingly overpowered. It is the reward for 150 deathless days and up to 10 players per server can hold it. If it proves too strong in play the dial to turn is the cooldown - not the title. Put the cooldown in the server config.
Meta-titles (PROPOSED) | Collector +2 - Archivist +4 - Chronicler +6. Slot-exempt and budget-exempt. They grant budget rather than stats. | Answers Open Question 13 without making the cap a config number. A player who has earned half the mod ends at 52 instead of 40 - about one extra Rare title's worth of room - and the collection itself becomes the progression track. Grant no raw stats or they double-dip.
Per-attribute hard caps | See table below | Second safety net. Even inside 40 points a player could dump everything into one attribute. Hard caps mean no single stat can run away.
Sample builds at the 40-point cap | Composition | Total
Broad generalist | 10 Common/Uncommon titles | ~25 - well under cap. Early game is unconstrained by design.
Balanced mid-game | 4 Rare + 4 Uncommon + 2 Common | ~39
Specialist | 4 Legendary | ~38 - four slots used - six empty. Depth over breadth.
Hybrid endgame | 2 Legendary + 3 Rare + 5 Common | ~42 - REFUSED. Drop one Common to fit.
Endgame veteran | 40 points equipped + 6 scarce titles | 40 + ~22 exempt = 62 effective. Feels earned rather than broken because the exempt 22 is mostly utility.
Attribute | Hard Cap From Titles | Note
max_health | +10.0 (5 hearts) | Vanilla is 20. This is a 50% ceiling.
armor | +4.0 | Two armor points is already meaningful
armor_toughness | +4.0
knockback_resistance | +0.4 | 1.0 is total immunity - never approach it
attack_damage | +25% | The single most sensitive number in the mod
attack_speed | +15% | Multiplies with attack_damage - keep it tight
movement_speed | +15% | Above 20% some server anti-cheat flags players
jump_strength | +15%
luck | +4.0
block_break_speed | +40% | Mining speed is low-risk - a generous cap is fine
mining_efficiency | +5.0
interaction range | +2.0 | PvP-sensitive
DMG_VS_TYPE per entity type tag | +30% | Per tag - not total across tags
DMG_RESIST_FROM_TYPE total | -40% | Sum across all sources. Stacking resistances to near-immunity is the classic break
potion duration | +50%
xp gain | +50%
fall damage reduction | -60% (before Unique exemptions) | First Dragonslayer's immunity is deliberately outside this
Implementation note | Enforce the budget cap in the equip handler on the SERVER. Refuse the equip and send a message. Never trust the client.
Implementation note | Enforce per-attribute caps at modifier-application time - after summing all equipped and scarce contributions - by clamping the final total.
Implementation note | Show remaining budget live in the Titles screen as "31 / 40". Players will optimise against it and that is the fun.
Implementation note | Every number here belongs in the server config so pack authors can rebalance without forking.

## Tweak Queue
Title ID | Display Name | Field | Concern | Options On The Table | Status | Added
vein_seeker | Vein Seeker | - | Flagged for a rethink - reason not written down yet | - | Undecided | 2026-08-11